## Estimates (hidden)
Application Name | Comments | Manual Test cases Available | Requirement doc Available | Manual Test case count | Update Test case | % Updation | Automation | Automation Test case | Time required for Automation | Time required for Manual Test design/updates | Requirement Analysis time | Test data creation | Manual Testing | Parallel Testing(Manual) | Smoke Execution & Failure Analysis | Defects & Retesting | Total
CART | Re-write the test plan | Y | Y | 19 | Y | 50% | Y | 19 | 9.5 | 2 | 2 | 1 |  | 5 | 1.45 | 1.45 | 22.4
Vision Poller |  | Y | N | 7 | Y | 50% | Y | 7 | 3.5 | 1 | 1 | 1 |  | 2 | 0.65 | 0.65 | 9.8
B2B Mortgage Admin (B2BMortgageAdmin) |  | Y | N | 10 | Y | 50% | Y | 10 | 5 | 1 | 2 | 1 |  | 2.5 | 0.9 | 0.9 | 13.3
B2B Mortgage MCR Agent (MCRAgent) | Not in scope | Y | N | 20 | Y | 50% | Y | 20 | 10 | 2 | 2 | 1 |  | 5 | 1.5 | 1.5 | 23
B2B Mortgage MCR Form (MCRForm) | Not in scope | Y | N | 12 | Y | 50% | Y | 12 | 6 | 1.5 | 2 | 1 |  | 4 | 1.05 | 1.05 | 16.6
ROAR UI (ROAR) |  | Y | N | 94 | Y | 50% | Y | 94 | 47 | 6 | 6 | 2 |  | 25 | 6.1 | 6.1 | 98.2
183.3
Activities |  | % Time planned |  | Time required for Automation ETM
Requirement Anaysis |  | 10 |  | Simple | Medium | Complex
Test plan updates |  | 10 |  | 2 | 1.5 | 1
Test data preparation |  | 5
Smoke Execution |  | 10
Manual Test Execution |  | 15 |  | Assumptions :
Full Functional Automation |  | 40 |  | 1. Team is well versed with ETF , if new folks then estimations have to be bumped by 30%
Defects & Retesting |  | 10 |  | 2. Applications are simple , max test steps is 4 steps per test case
3. Manual test design is available and we are going to update only 50%
4. All cases have to be automated
5. Test data creation is assumed to be straight forward or we have to pick up from Datasan tool.
6. Automation estimates is only for Test automation design , dry runs and execution is separate
7. Automation will not be done for Parallel Testing i.e. On Prem Application will not be automated.
8. This estimation is done without considering downtime

## All Apps - Estimations
[14 empty] | Manual - Effort (hrs) |  |  | Automation - Effort (hrs)
Category | Component Name | Status | Target Date Avail for Testing in Dev. Env. | Target Date | Remarks | Feature | Who is testing as of today? | Requirement Document available ? | Test plan available ? | # Screens | Complexity | External app Dependency ? | # Test cases | Analysis & Design | Execution & Retesting | Overall Effort | Analysis & Design | Automation Design | Re-execution & Retesting | Overall Effort | Risks
Web UI | CART (CARTUI) | Yet to Start |  |  | This is the one you're working on | Rewrite |  |  | NA
WebService | Carrier Feed Sync Svc (CarrierFeedSync.Service) | WIP | 2019-09-09 | 2019-09-30 | Server Upgrade | Commercial 2016 Server Migration | Haynes, Susie | Yes | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 16 | 2 | 22 | 1. Cannot be tested in lower environments as this service is to capture coverage details which does not have the set up in lower environments. Can be tested only in Prod environment 2. Cannot be automated due to data dependency on the partners.
WebService | Relay Service (System/SendMail) | WIP | 2019-09-09 | 2019-09-30 | Server Upgrade | Commercial 2016 Server Migration | TBD | No | No | NA | Complex | No | 15 | 12.5 | 7.5 | 20 | 4 | 16 | 2 | 22 | Need to reach out to McFarren for details. Given estimates are based on assumptions
Windows Services | B2B Mortgage Exchange Poller | WIP | 2019-09-09 | 2019-09-30 | Server Upgrade | Commercial 2016 Server Migration | TBD | No | No | NA | Complex | No | 15 | 12.5 | 7.5 | 20 | 4 | 16 | 2 | 22 | Need to reach out to McFarren for details. Estimations - TBD
Windows Services | Vision Poller | WIP | 2019-09-09 | 2019-09-30 | Server Upgrade | Commercial 2016 Server Migration | TBD | Yes | Yes | 2 | Simple | No | 7 | 4 | 3.5 | 7.5 | 2 | 4 | 2 | 8
WebService | ML Config Service (MultilineConfigurationSvc) | WIP | 2019-10-09 | 2019-10-30 | Azure Version Avaliable. On-perm to be sunset | Multiline Migrated App/Component Decommissioning | TBD | Yes | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 2 | 8 | 2 | 12 | Need to reach out to McFarren for details
Web UI | B2B Mortgage Admin (B2BMortgageAdmin) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Desktop Application | TBD | Yes | Yes | 3 | Simple | No | 10 | 4 | 5 | 9 | 4 | 6 | 2 | 12 | Analyst, Bobbie Baker used to test it.
Web UI | B2B Mortgage Email UI (B2BMortgageEmailUI) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | No | NA | 3 -Assuming | Simple | No | 15 | 5 | 4 | 9 | 2 | 10 | 2 | 14
Web UI | B2B Mortgage MCR Agent (MCRAgent) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD |  | NA | 3 -Assuming | Simple | No | 15 | 5 | 4 | 9 | 2 | 10 | 2 | 14
Web UI | B2B Mortgage MCR Form (MCRForm) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | NA | 4-Assuming | Medium | No | 20 | 7 | 5 | 12 | 3 | 10 | 4 | 17
Web UI | Client Recon Admin (MoatClientReconAdmin) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | Yes | No | 2 | Simple | No | 10 | 5 | 5 | 10 | 5 | 10 | 2 | 17
Web UI | Client Recon UI (MoatClientReconWeb) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | Yes | No | 2 | Medium | Yes | 15 | 9 | 9.9 | 18.9 | 9 | 12 | 3 | 24
Web UI | Client Tool UI (???) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | Yes | No | 2 | Medium | Yes | 15 | 9 | 9.9 | 18.9 | 9 | 12 | 3 | 24
Web UI | Moat Account Center UI (MoatAccountCenter) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | Yes | No | 2 | Simple | No | 30 | 16 | 15 | 31 | 16 | 24 | 5 | 45
Web UI | ROAR UI (ROAR) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | Yes | Yes | 4 | High | Yes | 94 | 24 | 78.02 | 102.02 | 24 | 70.5 | 16 | 110.5
WebService | B2B Automation Svc (PartnerAutomationService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | NA | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20 | Not in scope since UI consumes and it has been tested by GEICO. However, will confirm with Krish McFareen
WebService | B2B Mortgage Data Svc (B2BMortgageService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | NA | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20
WebService | B2B Mortgage Email Svc (B2BMortgage.EmailService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | NA | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20
WebService | Carrier Fuse Svc (CarrierFuseApi) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration | TBD | Yes | Yes | NA | Simple | No | 6 | 4 | 3 | 7 | 2 | 4 | 2 | 8 | Captures the real time metrics. As per the user guide, results verification is only to check the response is returned or not.
WebService | CASH API Svc (CASHApi) | Yet to Start |  | 2019-10-30 | Rewite - Estimation in-progress | Marked for Rewrite - OOS |  |  | NA | NA | Medium | Yes | 15 | 6 | 7.5 | 13.5 | 4 | 12 | 4 | 20
WebService | Client Real-Time Svc (ClientRealTimeApi) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20 | Client Recon UI is consuming this Service. Susie confirmed, however checking with Kris to confirm
WebService | Client Recon Svc (MoatClientReconService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20 | Client Recon UI is consuming this Service. Susie confirmed, however checking with Kris to confirm
WebService | Client Search Svc (ClientSearchService/v8.0) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20 | Client Recon UI is consuming this Service. Susie confirmed, however checking with Kris to confirm
WebService | ML Equality Integration Svc (MultilineEqualityIntegrationApi) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20
WebService | MOAT Account Center Data Svc (MACService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20 | Moat Account Center UI is consuming this Service. Susie confirmed, however checking with Kris to confirm
WebService | TSS Configuration Svc (TSSConfigService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20
WebService | TSS Data Svc (TSSDataService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20
WebService | TSS Document Storage Svc (DocStorageService) | Yet to Start | 2019-10-09 | 2019-10-30 | On-Prem to Azure Move - WIP | Multiline Azure Migration |  |  | No | NA | Complex | Yes | 15 | 12.5 | 7.5 | 20 | 4 | 12 | 4 | 20
[13 empty] | 477 | 285.5 | 262.32 | 547.82 | 140 | 372.5 | 99 | 611.5
Assumptions:
1. Comparison testing with legacy applications
2. Manual test design is available and we are going to update only 50%
3. ETF is an Automation tool
4. Team is well versed with ETF , if new folks then estimations will be bumped up by 30%
5. Automation will not be done for Parallel Testing i.e. On Prem Application will not be automated.
6. Automation execution is unattended mode
7. 'Test plan available no' component has 15 cases, is based on average web service test design across projects
Activities:
1. Manual - Analysis & Design includes analysis & understanding of the application and database, clarifications resolution, test data identification, test design, reviews, and rework
2. Manual - Execution & Retesting includes test execution, re-execution, result analysis, database validations, defect management, retest and rework
3. Automation Design includes mapping and capturing UI object properties, design ETF test case, dry run, updates, and rework
4. Automation - Execution & Retesting includes automation execution, result analysts, database validations, defect management, retesting
5. Re-execution & Retesting includes failure analysis, defect management and retesting
6. Re-execution & Retesting includes failures analysis, re-execution and retesting
Complexity and Analysis Time (per resource):
1. Simple - <=15 Test Cases - 5 hrs
2. Medium - >15 to <=30 Test Cases - 10 hrs
3. High - >30 Test Cases - 15 hrs
Execution time based on complexity:
1. Simple - 30 mins
2. Medium - 40 mins
3. High - 50 mins
4. WebService - 20 mins
Effort calculation
1. Analysis & Design - Complexity and Analysis Time + 50% of # Test Cases
2. Execution & Retesting - # Test Cases * Execution time based on complexity
3. Add ~25% of time to the Overall effort for training, co-ordination, calls/meetings, envrironmental issues/downtime etc.,
4. Re-execution & Retesting - 10% of Automation Design

## Plan
| Effort (hours) | Effort (Person days)
Manual Effort | 547.82 | 68.4775
Automation effort | 611.5 | 76.4375
Total | 1159.32 | 144.915
Buffer & Extra effort | 347.796
1507.116
|  |  | Sprint | Activities | Estimated hours | Resources | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov | Dec
Date | Appplication available for Testing |  |  |  | Effort (hours) |  | Wk1 (1st Jul - 7th Jul) | Wk2 (8th - 14th Jul) | Wk3 (15th - 21st Jul) | Wk4 (22nd Jul - 28th Jul) | Wk1 (29th Jul - 4thAug) | Wk2 (5th Aug - 11thAug) | Wk3 (12th Aug- 18thAug) | Wk4 (19thAug - 25th Aug) | Wk5 (26th Aug - 1st Sep) | Wk1 (2nd Sep - 8th Sep) | Wk2 (9th Sep - 15th Sep) | Wk3 (16th Sep - 22th Sep) | Wk4 (23rd Sep - 29th Sep) | Wk1 (30th Sep - 6th Oct ) | Wk2 (7th Oct -13th Oct ) | Wk3 (14th Oct -20th Oct) | Wk4 (21st Oct - 27th Oct ) | Wk5 (28th Oct - 3rd Nov ) | Wk1 (4th Nov - 10th Nov)
2019-09-09 | 4 |  | Sprint 0 | Test design/Automation for 5Apps | 140 | 2 QA
2019-09-10 | 22 |  | Sprint 1 | Test design/Automation for 5 Apps | 140 | 2 QA
|  |  | Sprint 3 | Test design/Automation for 8 Apps | 140 | 2 QA
|  |  | Sprint 4 | Test design/Automation for 8 Apps | 140 | 2 QA
|  |  | Sprint 5 | Test design/Automation for 2 Apps and Buffer for backlog | 210 | 3 QA
|  |  | Sprint 6 | Execution for 4 App | 210 | 3 QA
|  |  | Sprint 7 | Execution for 10 App | 210 | 3 QA
|  |  | Sprint 8 | Execution for 10 App | 210 | 3 QA
|  |  | Sprint 9 | Execution for 2 Apps and Bug Bash | 140 | 2 QA
|  |  |  | Total hours | 1540

## Sheet2
Carrier Feed : This would include PIF (Policy in Force), daily New Business reporting, and other relevant policy level details bound by GEICO and written by its Partners.
The data contract portion of this document includes specific data definitions for all detail that GEICO will expect within a PIF data feed. The SLA portion of this document will define business rules that govern when a data feed will be sent, the actions taken on a Policy that trigger a data feed, and any technical specifications that are required for a data feed to be correctly processed by GEICO systems.
For this data feed, we are focusing specifically on Wind or Flood policies. In the future we may address other existing or planned policy forms.