## Religare_Estimates
SCREEN WISE ESTIMATION
Screen Name | Total Test cases | Low | Medium | Complex | Duration (hrs) | Duration (Man Days) | Start Date | End Date
Home Page | 17 | 10.2 | 6.8 | 0 | 46.5375 | 6.6482
Care | 90 | 54 | 36 | 0 | 246.375 | 35.1964
Care Super Server | 37 | 22.2 | 14.8 | 0 | 101.2875 | 14.4696
Care-Global(Faveo) | 51 | 30.6 | 20.4 | 0 | 139.6125 | 19.9446
Care Freedom | 40 | 24 | 16 | 0 | 109.5 | 15.6429
Secure | 53 | 31.8 | 21.2 | 0 | 145.0875 | 20.7268
Assure | 36 | 21.6 | 14.4 | 0 | 98.55 | 14.0786
Explore | 84 | 50.4 | 33.6 | 0 | 229.95 | 32.85
Student Explore | 88 | 52.8 | 35.2 | 0 | 240.9 | 34.4143
Joy Today | 30 | 18 | 12 | 0 | 82.125 | 11.7321
Joy Tomorrow | 36 | 21.6 | 14.4 | 0 | 98.55 | 14.0786
Enhance | 41 | 24.6 | 16.4 | 0 | 112.2375 | 16.0339
Total Time | 603 | 827.6175 | 823.095 | 0 | 1650.7125 | 235.8161
Assumptions :
1. This estimates are based on Complexity , we are assuming that 30% Simple , 40% Medium and 30% Complex.
2. In this estimation we have assumed that control and scripts can be reused and we are considering reusability factor as 40%.
3. These estimates are based on the assumption that Test cases are ready to be automated and we don't have to do any rework on Test design.
4. These estimates are high level estimates based on assumptions , after detailed analysis of the scripts these estimates may change.
5. Activities considered for Test script Analysis are : Understanding the script , functionality , manually executing the script , If any doubts getting clarifications .
6. Automation Test design effort include following activities : Automating Navigations , Controls and Datasheet updates, Test Data Setup
7. This estimates are based on assumption that there ae no Third party integrations or applications involved.
8. Estimations have factored the time for Database validations.
9. The above estimaions are based on the assumption that all the test case provided are regression cases and all can be automated .
10. These estimates are not provided for any test cases which includes Batch job or Desktop applications . These are purely for web based applications involving Selenium.

## Estimation Basis
Complexity | Screens | Controls | DB validations | Third Party Integration | Datasheet (Field)
Low | <=5 | <=20 | <=5 |  | <=15
Medium | >5 & <=10 | >20 & <=30 | >5 and <=15 |  | > 15 & <25
Complex | >10 & <=15 | > 30 and <=45 | >15 and <=25 |  | >25 and <=35
Test case Design and Execution Complexity Matrix | [5 empty] | Comments
|  |  | Simple | Medium | Complex
Test script analysis |  |  | 0.5 | 0.75 | 1
Automation Test Design (hr) |  |  | 1.9167 | 2.75 | 4.6667
Control Id Identification (Xpath) |  |  | 0.66667 | 1 | 1.5
Review & rework |  |  | 0.47917 | 0.6875 | 1.1667
Dry Run |  |  | 0.25 | 0.5 | 0.75
Resuability % |  |  | 40 | 40 | 40 | Assuming that resuability is 40%
Total time |  |  | 3.8125 | 5.6875 | 9.0833
After considering Reusability Total Time |  |  | 2.2875 | 3.4125 | 5.45
Note on C11: Swaroop Reddy Yeturu: Understanding the script , functionality , manually executing the script , If any doubts getting clarifications .
Note on C12: Swaroop Reddy Yeturu: Automating Navigations , Controls and Datasheet updates, Test Data Setup
Note on F12: Swaroop Reddy Yeturu: in Hrs 2 min * 5 Pages (Navigation) + 20 control * 2 min(for automating controls) + 15 *1 (updating Data sheet) + 5 DB Validations * 5 min =(2*5+20*2+15*1+5*5)/60
Note on G12: Swaroop Reddy Yeturu: Swaroop Reddy Yeturu: in Hrs 5 min * 10 Pages (Navigation) + 20 control * 2 min(for automating controls) + 30 * 1 (updating Data sheet) + 15 DB Validations *10 =(2*10+20*2+30+15*5)/60
Note on H12: Archana Agarwal: 15 screens *2 + 45 controls *2 + 25 DB *5 +35*1 (Data sheet) = (15*2 + 45*2+25*5 + 35*1)/60