## Slide 1
DirectNet Application Modernization Kick-Off Meeting - 11/8/2017

## Slide 2
Project Overview
Project Contact Details
Applications In Scope
Application Contacts Required
Indicative High level schedule
Testing Approach
Next 2 months Schedule
Communication Plan
Application owners support required
Agenda

## Slide 3
Project Overview
Migrate all the identified legacy DirectNet Applications to Azure PaaS through one of the following approaches
  Migrate .Net Framework 4.x applications to Azure PaaS
  Migrate legacy applications (that have source code available) to .NET Framework 4.5.2
  Reverse engineer the applications with no source code and upgrade them to latest .NET framework 4.5.2
Document the As-Is functionality of the application
Develop automated Test suites of the application
Setup Monitoring and alerts
Applications will be ready for Production implementation latest by Oct 2018
  Discovery & Assessment will be completed by Jan 5th 2018
  UAT Schedule will be communicated in Jan 2018
  First set of applications will be ready for User Acceptance testing by February 2018
  Sunset the on-premises applications by Nov 2018
Provide Knowledge Transition and Training as required to Application Owners

## Slide 4
Project Contact Details
  Sponsor : Fikri Larguet, FLarguet@geico.com
  Manager : Mario Naranjo, MNaranjo@geico.com
  Project Manager : Varaprasad Pasumarthi, Vpasumarthi@geico.com
  Project Lead : Ivan Reinafarje, IReinafarje@geico.com
  Architect : Phillip Dyson, Pdyson@geico.com
  Project Contact Email : DirectNetModernizationTeam@geico.com
  SharePoint Site : DirectNetModernization
  Project ID to Charge : 8428-2018 Data Center Evacuation Engineering
  Project Start Date : Nov 6th 2017

## Slide 5
33 Applications require contact details
Underwriting, Claims & Financial Systems have the major applications that need to be migrated
Applications In Scope
Chart: 
| TBD | Financial Systems | Underwriting | Claims | Policy | Client | Service | Desktop Systems and Distribution | Billing | NOC | Knowledge Management | Enterprise Security | Human Resources | Telecom | Sales | Data Sanitization | Planning & Budgeting | CALG | Business Messaging | ITSM | Imaging and MFT
Marked for Decommisioning | 17 | 5 | 4 | 1 | 1 | 7 | 8 | 2 | 1 | 1 | 2 | 2 | 2 | 1
Targeted for Migration | 33 | 24 | 20 | 16 | 8 | 1 | 5 | 5 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1
Chart: 
| Grand Total
 | 54
 | 127

## Slide 6
AutomatedDispatch
Systems Error Report Form
Test Info Update(SelectionTests)
Demand & Lawsuit Log Home
Sales Call Back Reminder System
Claims Provider Profile Management
SOD Tape Library Mailer Request
GeicoSelectionTests
Help Desk Customer Service Satisfaction Survey
Ideas for Quality
V8 Online Documentation
CSMCollector
CSR Call Driver
Forcedownload
Score Card Summary Report
Iowa/Coralville/Associate Lookup
Approval Authority/Sales SOB Table reqeusts
Section Move / Status Change
Region IV Departments
AC98 Refund Request
Region IV/CashVoucher
R4 Manual Quote
Region 4 Service PMT Application
Region 4 Supervisor Goal Grading
Region 4 SAS
Region6/Claims/CSR/Monitor
Region I Home Page
GeoWebService
Services/RentalWAS
Services/Reporting/InterviewTracking
CA Stat Reporting
Controller Home Page
StaffDepartments/QualityAdministration/IQ
Application Contacts Required

## Slide 7
Indicative High Level Schedule
Design and Execute & Migrate
Each Release will spread across 3 to 4 Sprints with 3 weeks each
Continuous UAT will start after the first Sprint
Review and acceptance of Test cases
Perform UAT Testing & provide acceptance
Design, Development and QA testing will be performed
Walk through sessions with Application owners – code, application, deployment
Discovery & Assess
Applications will be documented
Non-functional requirements will be elicited
Overview of the Applications by owners
Walk through sessions with owners
Acceptance of Requirements/Test Strategy
Prioritize the list of applications by Release
Hyper-care
Hyper-care is extended at the end of every release cycle, for the applications rolled out in production
Transition and parallel support with Application owners
* Application level release dates will be prioritized as part of the Discover Phase in review with owners
Blue Highlighted Tasks represent the Application owners Involvement during the Project, Communication will be sent with date

## Slide 8
Indicative Applications Priority by Area/Release
Release1
  Financial Systems
  Knowledge Management
  Billing
Release 2
  Billing
  Claims
  Underwriting
  Policy
  Desktop Systems & Distribution
  Enterprise Security
Release 3
  Sales
  Human Resources
  Knowledge Management
  Client
  ITSM
  Business Messaging
  NOC
Release 4
Unidentified Applications
* Its an Indicative Priority, Applications Priority will be finalized during the Discovery & Assessment

## Slide 9
End to End traceability in VSTS
Sprint Testing
v
Early Defect detection
v
Ability to Support daily
builds
v
Adherence to planned
schedules and budgets
Release N
Sprint 1
Sprint 2
Sprint 3
W1
W2
W3
W1
W2
W3
W1
W2
W3
ü
Completed
acceptance criteria
ü
Completed non
acceptance criteria
ü
Optimize test cases
ü
Automat test cases
ü
Completed acceptance
criteria
ü
Completed non
acceptance criteria
ü
String S1 + S2
ü
Optimize test cases
ü
Automat test cases
AUTOMATED SMOKE TESTING (on
-
demand)
EXPLORATORY TESTING
FUNCTIONAL TESTING
INTEGRATION & REGRESSION TESTING
CONTINUOUS EXECUTION
Testing Approach
VSTS
VSTS

## Slide 10
Reverse Engineer the Assemblies
Meet with Application Owners
Identify risks, dependencies and constraints
Kick Off Meeting
Access current environment & code repositories
Understand business functionality & identify key components
Documentation of Applications
Prioritize &
Release Planning
Discovery Phase Schedule
Next 2 Months Schedule

## Slide 11
Financial Systems
December
Knowledge Management
November
Business Messaging
Underwriting
Sales
Desktop Systems & Distribution
Enterprise Security
Human Resources
ITSM
NOC
Unidentified areas
Billing
Claims
Policy
Client
Human Resources
Discovery – Application Area Schedule

## Slide 12
Contact Email for Questions: DirectNetModernizationTeam@Geico.com
SharePoint will be updated on regular basis on the updates of the Project and Application Release Schedule
Planned Meetings & Frequency
  Sprint Retrospective & Review meeting for each Sprint (3 weeks)
  Monthly Scrum of Scrums with Sponsor & Key stakeholders
  Quarterly Stakeholder Meetings with Application Owners
Communication Plan

## Slide 13
Support we need from Application owners
Help required in providing business overview of the applications
Help with identifying any dependencies for the application migration
Review & accept the documented functional specifications
Review and accept the Test cases in VSTS
Perform User Acceptance Testing and provide the acceptance to deploy the migrated application
Quick turn-around for timely reviews/clarifications to the DirectNet Migration team
  ETAs will be shared during the discussion with the application owners

## Slide 14
Transition
Understand the usage of application and SLA
Understand any pending changes or plans for changes
Understand any non-functional requirements
Present the understanding of application
Prioritize applications rollout, discuss the roadmap and timelines
Design walk through
Discuss Subscription cost, Topology, setting up Alert distribution list
Changes needs to be made and communicated to User
Database porting strategy
Plan the Go-Live Date & Sunset Dates
Test and provide acceptance of the application
Communication with new URLs and instructions
Verify the application in production
Sun set the on-premises instances
Outcome
Requirement Specification Document
Test cases in VSTS, traceability to user stories in VSTS, automated test suite
Migrated code base in Azure & VSTS
Monitoring & Alerting information ( Splunk, OMS & AppInsight)
Azure Subscription information
Runbooks for L1/NOC teams
Application Owners Involvement & Knowledge Transition

## Slide 15
THANK YOU