## Sheet1
S.No | Phase | Audit Item | Description | Objective | Metrics | Comments | 6th Feb 2018 | 16th Jan 2018
1 | Sprint Planning | User Stories | How are we assigning Story Points to User stories | Improve estimation |  | establish guidelines and share with team, such as testing tasks for parallel test execution |  | Guidelines created for Simple , Medium and Complex application w.r.t. QA & Dev hrs . 2 hrs per story point .
2 | Sprint Planning | Estimation | How estimates are being done for User stories | Improve estimation |  | establish guidelines and share with team, such as testing tasks for parallel test execution |  | Guidelines created.
3 | Sprint Planning | Estimation | Is Capacity Planning considered while doing estimation | Improve estimation |  |  |  | QA : Yes , Dev : Yes
4 | Sprint execution | VSTS Tasks | Tasks created for User stories or not | Traceability/Coverage |  |  |  | QA : Yes , Dev : Not all tasks are created
5 | Sprint execution | VSTS Tasks | Tasks Naming should be consistent so that report generation is seamless | Input for Metrics generation |  |  |  | QA : Yes , Dev : Yes
6 | Sprint execution | VSTS Tasks | Tasks Planned hrs should be filled | Improve estimation and Progress monitoring |  | C |  | QA : Yes , Dev : Yes
7 | Sprint execution | VSTS Tasks | Tasks should be associated with a User story | Traceability/Coverage |  |  |  | QA : Yes , Dev : WIP
8 | Sprint execution | VSTS Tasks | Defect Retesting Tasks should be Created | Rework effort |  | All efforts pertaining to defect retesting or Test execution will go in this task. |  | QA : Yes , Dev : WIP
9 | Sprint execution | VSTS Tasks | Team has updated actual hrs , planned and actual execution test cases count are updated in VSTS Tasks. | Traceability/Coverage, Input for Metrics generation | Test Design Productivty and Test Execution Productivity |  |  | QA : WIP , Dev : WIP
10 | Sprint execution | Test execution | Ensure that all test cases are executed . Results , snapshots are attached in VSTS. | Traceability/Coverage, Input for Metrics generation | Test Pass , Fail % |  |  | QA : WIP , Dev : WIP
11 | Sprint execution | Smoke | Smoke Test cases identified and automated in the First week of Sprint | Good build release for QA testing, Process adherence |  |  |  | QA: 3/8 Applications Smoke tests are ready.
12 | Sprint execution | Automation | Identification of regression/automable cases is completed or not. | Regression tests identification | Regression% |  |  | QA: 3/8 Applications Smoke tests are ready.
13 | Sprint execution | Automation | Automation completion % for each application should be >=90% | Full Regression coverage | Automation% |  |  | QA : WIP
14 | Sprint execution | Mini Regression | Mini Regression cases should be identified by 1st week of Sprint. (30% of Full regression) | Mini Regression coverage | Automation% |  |  | QA: 1/8 Applications Smoke tests are ready.
15 | Sprint execution | Automation | DB and Webservices automation is completed for respective applications or not. | Automation of DB and Services | Automation% |  |  | QA : Testing not started as code not deployed
16 | Sprint execution | Defect Logging | Team is logging defect as per the defined process | Defect Proccess adherence |  |  |  | QA : Testing not started as code not deployed
17 | Sprint execution | Defects | Defects are attached to User story or not | Process adherence |  |  |  | QA : Testing not started as code not deployed
18 | Sprint execution | Defects | Defect Ageing | Open defects | Defect Ageing |  |  | QA : Testing not started as code not deployed
19 | Sprint execution | Reviews | Test case Review & Updates are happening properly or not | Test Coverage | Scenario Slippage | Should be below 5% (Scenarios missed / Total scenarios) |  | QA : Review completed for 1/8 applications .
20 | Sprint execution | Reviews | automation completion % for each application should be >=90% | Process adherence, Results review |  |  |  | QA : Testing not started as code not deployed
21 | Sprint execution | Reviews | BA's are doing Test results review and sign-off | Process adherence, Sign-off |  |  |  | QA : Testing not started as code not deployed
22 | Sprint execution | Exploratory Testing | Exploratory Testing is happening or not. How many defects raised while doing Exploratory Testing . | To identify Requirements missed in Discovery phase. | Exploratory testing defects vs total defects | Valid Exploratory Defects means that we have missed to capture all the requirements . |  | QA : Testing not started as code not deployed
23 | Sprint execution | Parallel Execution | Parallel Execution : How many defects we raised. | Modernized application is "as-is" in comparison to legacy | Parallel execution defects Vs Total defects. |  |  | QA : Testing not started as code not deployed
24 | Sprint execution | Integration testing | Integration w.r.t. other applications are tested or not. | Process adherence |  |  |  | QA : Testing not started as code not deployed
25 | Sprint execution | Defects | Review of invalid defects | Review of invalid defects | Invalid defects % |  |  | QA : Testing not started as code not deployed
26 | Sprint execution | Defects | RCA of production reported defects | RCA of defects reported | Defect Slippage |  |  | QA : Testing not started as code not deployed
27 | Sprint execution | Defects | UAT defects | review of UAT defects |  |  |  | QA : Testing not started as code not deployed
28 | Sprint execution | Sprint Progress | Review of user stories delivered with in a Sprint and Release | Story points committed vs delivered | Velocity |  |  | WIP
29 | Sprint execution | Defects | How many regression defects were raised in Full Regression in a Sprint . | Rework effort | Regression Defects Vs Functional defects for a Application . |  |  | QA : Testing not started as code not deployed
30 | Sprint execution | Daily work plan and monitoring | Replan the work for QA Team in case of any delay in Deployments . | Effective utilization of team |  |  |  | QA : V4 Test authoring , Mini Regresion identification , Next Sprint Test case writing , Test data setup for different Roles . Dev : Waiting time as deployed issues are yet to be resolved. Team will take up next User stories.
Note on D5: Archana Agarwal: Requirement Analysis Functional test design and test data Test case review Test case update Manual test execution Automation of test cases Automation dry run and updates Defect Logging & Defect Retesting Parallel testing for application End to end testing Mini regression Full regression exploratory testing Creation of Object Repository