## Guidelines
ValueMomentum
QA PROJECT- INTERNAL AUDIT REPORT-GUIDELINES
S. No. | Guidelines
1 | Use standard date format DD-Mon-YYYY where ever applicable.
2 | Description of Audit Finding should be precise and self-explanatory, pointing towards the implementation deficiency. Provide the details of the sample referred as basis, where the deficiency has been identified.
3 | If the deficiency is identified against the requirement, the status should be changed to 'No'. Else this should be 'Yes'.
4 | If the deficiency is observed as closed during following audit, do not change the status to 'Yes'. Instead, update the Actual Closure Date and Closure Comments.
5 | Ensure that the root cause is pointing towards the specific reason for not meeting the requirement.
6 | Ensure that the corrective action is addressing how the deficiency being addressed and how it will be ensured avoiding recurrence of the same.
7 | Do not change or tamper the format.
8 | Once the audit is done, ensure updating Business Unit, Account, Project Name, Project Type, Project Manager, Milestone, Lifecycle Phase, Audit Cycle, Auditor, Audit Date, Preparation Effort, Audit Effort, Follow up Audit Date, From Time, To Time, Description of Finding, Status (Yes, No,NA), Follow up audit date, if any.
9 | Once the follow up audit is done, ensure updating Actual Closure Date and Closure Comments.
10 | Before publishing the audit report, run the spell checking tool and address the issues, if any. Also save the document so that PC Dashboard sheet open if any one opens the report.

## PC Dashboard
ValueMomentum
QA/TESTING PROJECT PROCESS COMPLIANCE DASHBOARD Version 6.0
[10 empty] | Cycle 1 |  | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5
| Business Unit | Account | Project Name | Project Type | Cycle 1-PCI | Cycle 2-PCI | Cycle 3-PCI | Cycle 4-PCI | Cycle 5-PCI | Critical | 12 | 0 | 0 | 0 | 0
| CS US | GEICO | MSI_NB | Testing/QA | 65.26% | 100% | 100% | 100% | 100% | Major | 16 | 0 | 0 | 0 | 0
| Project Manager | Milestone | Lifecycle Phase | Audit Cycle | Auditor | Audit Date | Preparation Effort | Audit Effort | Follow up | Minor | 6 | 0 | 0 | 0 | 0 | From Time to Time
| Archana Agarwal |  | Testing | Cycle 1 | Devi Prasad | 2015-10-15 | 15 Mins | 90 Mins | 2015-10-28 | [6 empty] | 2 PM to 3:30 PM
| Vital Few Critical Many |  |  |  |  | Revenue Leakage Reduction Compliance Status
| PDCA wise PCI Status |  |  |  |  | Phase wise PCI Status

## Summary
PROJECT PROCESS COMPLIANCE SUMMARY
Criticality wise Status
Phase wise PCI Status | [6 empty] | Area | Cycle 1 |  |  | Cycle 2 |  |  | Cycle 3 |  |  | Cycle 4 |  |  | Cycle 5
Phase | Goal PCI | Cycle 1 PCI | Cycle 2 PCI | Cycle 3 PCI | Cycle 4 PCI | Cycle 5 PCI |  | Critical | Major | Minor | Critical | Major | Minor | Critical | Major | Minor | Critical | Major | Minor | Critical | Major | Minor
Project Initiation | 100% | 100% | 100% |  |  |  | Project Initiation
Project Management Plan | 100% | 66.1% | 100% |  |  |  | Project Management Plan | 6 | 9 | 3
Monitoring & Control | 100% | 38.96% | 100% | 100% | 100% | 100% | Monitoring & Control | 6 | 6 | 2
Test Requirements | 100% | 100% | 100% |  |  |  | Test Requirements
Test Design | 100% | 77.78% | 77.78% | 100% | 100% | 100% | Test Design |  | 1 | 1
Test Automation | 100% | 100% | 100% | 100% | 100% | 100% | Test Automation
Testing | 100% | 100% | 100% | 100% | 100% | 100% | Testing
Delivery | 100% | 100% | 100% |  |  |  | Build & Delivery
Project Closure | 100% | [5 empty] | Project Closure
Revenue Leakage Reduction Compliance Status
Area | Goal PCI | Cycle 1 PCI | Cycle 2 PCI | Cycle 3 PCI | Cycle 4 PCI | Cycle 5 PCI
Preventive compliance | 100% | 80.77% | 100% | 100% | 100% | 100%
Detective compliance | 100% | 81.25% | 100% | 100% | 100% | 100%
Internal Failure compliance | 100% |  | 100% | 100% | 100% | 100%
External Failure compliance | 100%
PDCA wise PCI Status
Area | Goal PCI | Cycle 1 PCI | Cycle 2 PCI | Cycle 3 PCI | Cycle 4 PCI | Cycle 5 PCI
Plan | 100% | 71.43% | 100% | 100% | 100% | 100%
Do/Implement | 100% | 65.75% | 100% | 100% | 100% | 100%
Check/Verify | 100% | 37.7% | 100% | 100% | 100% | 100%
Act/Improve | 100% | 20% | 100% | 100% | 100% | 100%

## Process Area wise
PROCESS AREA WISE COMPLIANCE STATUS
Phase | Process Areas | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Phase | Process Areas | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5
Project Initiation | Statement of Work | 100% | 100% |  |  |  | Test Requirements | Requirements Development | 100% | 100%
| Project Initiation Note | 100% | 100% |  |  |  |  | Requirements Analysis and Validation | 100% | 100%
| Project Kick Off | 100% | 100% |  |  |  |  | Requirements Traceability | 100% | 100%
Project Management Plan | Assumptions & Constraints | 100% | 100%
| Estimation | 93.33% | 100%
| Process Plan/Tailoring | 50% | 100% |  |  |  | Test Design | DAR |  | 100% | 100% | 100% | 100%
| IT/Human Resource Plan | 87.5% | 100%
| Skill Assessment | -37.5% | 100% |  |  |  |  | Product Integration Plan |  | 100% | 100% | 100% | 100%
| Schedule | 0% | 100% |  |  |  |  | Test Plan | 55.56% | 100% | 100% | 100% | 100%
| Configuration Management Plan | 61.9% | 100% |  |  |  |  | Unit Test Cases |  | 100% | 100% | 100% | 100%
| Access Permissions | 100% | 100% |  |  |  |  | Integration Test Cases |  | 100% | 100% | 100% | 100%
| Backup Plan | 100% | 100% |  |  |  |  | System Test Cases | 100% | 100% | 100% | 100% | 100%
| Change Management Plan | 100% | 100% |  |  |  |  | Regression Test Cases |  | 100% | 100% | 100% | 100%
| Metrics Plan | 0% | 100% |  |  |  | Test Automation | Load/Performance Test Scenarios |  | 100% | 100% | 100% | 100%
| Work Product Review & Audit Plan | 100% | 100%
| Risk Management Plan | 66.67% | 100%
| Stakeholder Commitment Plan | 100% | 100%
| Status Review Plan | 0% | 100% |  |  |  |  | Automation Framework | 100% | 100% | 100% | 100% | 100%
| DAR Plan | 100% | 100% |  |  |  |  | User Documentation |  | 100% | 100% | 100% | 100%
| Escalation Mechanism | 100% | 100%
| Reusable Components | 100% | 100% |  |  |  | Testing | Build for Integration Testing |  | 100% | 100% | 100% | 100%
| Project Closure Plan | 100% | 100% |  |  |  |  | Integration Testing |  | 100% | 100% | 100% | 100%
| Project Management Baseline | 0% | 100% |  |  |  |  | Build for System Testing |  | 100% | 100% | 100% | 100%
[8 empty] | System Testing | 100% | 100% | 100% | 100% | 100%
Monitoring & Control | Configuration Audits | 28.57% | 100% | 100% | 100% | 100% |  | Build for Regression Testing |  | 100% | 100% | 100% | 100%
| Access Permissions | 100% | 100% | 100% | 100% | 100% |  | Regression Testing |  | 100% | 100% | 100% | 100%
| Backups | 0% | 100% | 100% | 100% | 100% |  | Build for Load/Performance Testing |  | 100% | 100% | 100% | 100%
| Change Management |  | 100% | 100% | 100% | 100% |  | Load/Performance Testing |  | 100% | 100% | 100% | 100%
| Metrics | 0% | 100% | 100% | 100% | 100%
| Risk Management | 0% | 100% | 100% | 100% | 100%
| Issue Management | 0% | 100% | 100% | 100% | 100% | Delivery | Acceptance | 100% | 100%
| Actiion Item Tracking |  | 100% | 100% | 100% | 100%
| Review Defect Tracking | 0% | 100% | 100% | 100% | 100%
| Test Defect Tracking | 100% | 100% | 100% | 100% | 100% | Project Closure | Project closure activities
| Internal Audit Findings Tracking | 100% | 100% | 100% | 100% | 100%
| Trainings | 100% | 100% | 100% | 100% | 100%
| Status Reviews | 0% | 100% | 100% | 100% | 100%
Phase | Process Areas | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5
Project Initiation | Statement of Work | 0 | 0 | 0 | 0 | 0
| Project Initiation Note | 0 | 0 | 0 | 0 | 0
| Project Kick-off | 0 | 0 | 0 | 0 | 0
Project Management Plan | Assumptions & Constraints | 0 | 0 | 0 | 0 | 0
| Estimation | 1 | 0 | 0 | 0 | 0
| Process Plan/Tailoring | 2 | 0 | 0 | 0 | 0
| IT/Human Resource Plan | 1 | 0 | 0 | 0 | 0
| Skill Assessment | 3 | 0 | 0 | 0 | 0
| Schedule | 1 | 0 | 0 | 0 | 0
| Configuration Management Plan | 2 | 0 | 0 | 0 | 0
| Access Permissions | 0 | 0 | 0 | 0 | 0
| Backup Plan | 0 | 0 | 0 | 0 | 0
| Change Management Plan | 0 | 0 | 0 | 0 | 0
| Metrics Plan | 3 | 0 | 0 | 0 | 0
| Work Product Review and Audit Plan | 0 | 0 | 0 | 0 | 0
| Risk Management Plan | 1 | 0 | 0 | 0 | 0
| Stakeholder Commitment Plan | 0 | 0 | 0 | 0 | 0
| Status Review Plan | 1 | 0 | 0 | 0 | 0
| DAR Plan | 0 | 0 | 0 | 0 | 0
| Escalation Mechanism | 0 | 0 | 0 | 0 | 0
| Reusable Components | 0 | 0 | 0 | 0 | 0
| Project Closure Plan | 0 | 0 | 0 | 0 | 0
| Project Management Baseline | 3 | 0 | 0 | 0 | 0
Monitoring & Control | Configuration Audits | 1 | 0 | 0 | 0 | 0
| Access Permissions | 0 | 0 | 0 | 0 | 0
| Backups | 2 | 0 | 0 | 0 | 0
| Change Management | 0 | 0 | 0 | 0 | 0
| Metrics | 4 | 0 | 0 | 0 | 0
| Risk Management | 1 | 0 | 0 | 0 | 0
| Issue Management | 1 | 0 | 0 | 0 | 0
| Action Item Tracking | 0 | 0 | 0 | 0 | 0
| Review Defect Tracking | 1 | 0 | 0 | 0 | 0
| Test Defect Tracking | 0 | 0 | 0 | 0 | 0
| Internal Audit Findings Tracking | 0 | 0 | 0 | 0 | 0
| Trainings | 0 | 0 | 0 | 0 | 0
| Status Reviews | 4 | 0 | 0 | 0 | 0
Test Requirements | Requirements Development | 0 | 0 | 0 | 0 | 0
| Requirements Analysis & Validation | 0 | 0 | 0 | 0 | 0
| Requirements Traceability | 0 | 0 | 0 | 0 | 0
Test Design | DAR | 0 | 0 | 0 | 0 | 0
| Product Integration Plan | 0 | 0 | 0 | 0 | 0
| Test Plan | 2 | 0 | 0 | 0 | 0
| Unit Test Cases | 0 | 0 | 0 | 0 | 0
| Integration Test Cases | 0 | 0 | 0 | 0 | 0
| System Test Cases | 0 | 0 | 0 | 0 | 0
| Regression Test Cases | 0 | 0 | 0 | 0 | 0
| Load/Performance Test Scenarios | 0 | 0 | 0 | 0 | 0
| Unit Testing | 0 | 0 | 0 | 0 | 0
| User Documentation | 0 | 0 | 0 | 0 | 0
Testing | Build for Integration Testing | 0 | 0 | 0 | 0 | 0
| Integration Testing | 0 | 0 | 0 | 0 | 0
| Build for System Testing | 0 | 0 | 0 | 0 | 0
| System Testing | 0 | 0 | 0 | 0 | 0
| Build for Regression Testing | 0 | 0 | 0 | 0 | 0
| Regression Testing | 0 | 0 | 0 | 0 | 0
| Build for Load/Performance Testing | 0 | 0 | 0 | 0 | 0
| Load/Performance Testing | 0 | 0 | 0 | 0 | 0
0 | Acceptance | 0 | 0 | 0 | 0 | 0
Project Closure | Project Closure Activities | 0 | 0 | 0 | 0 | 0
Total |  | 34 | 0 | 0 | 0 | 0

## Severity wise
SEVERITY WISE COMPLIANCE STATUS
Phase | Process Area | Cycle 1 Applciable Weightage | Cycle 1 NCs |  |  | Cycle 2 Applciable Weightage | Cycle 2 NCs |  |  | Cycle 3 Applciable Weightage | Cycle 3 NCs |  |  | Cycle 4 Applciable Weightage | Cycle 4 NCs |  |  | Cycle 5 Applciable Weightage | Cycle 5 NCs
|  |  | Critical | Major | Minor |  | Critical | Major | Minor |  | Critical | Major | Minor |  | Critical | Major | Minor |  | Critical | Major | Minor
Project Initiation | Statement of Work | 5 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Initiation Note | 6 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Kick Off | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management | Assumptions & Constraints | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimation | 15 | 0 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Process Plan/Tailoring | 16 | 1 | 1 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IT/Human Resource Plan | 8 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill Assessment | 8 | 1 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Schedule | 5 | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Configuration Management Plan | 21 | 1 | 1 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Access Permissions | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backup Plan | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Change Management Plan | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Metrics Plan | 11 | 1 | 2 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Work Product Review & Audit Plan | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Risk Management Plan | 9 | 0 | 1 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stakeholder Commitment Plan | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Status Review Plan | 5 | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DAR Plan | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Escalation Mechanism | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reusable Components | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Closure Plan | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Management Baseline | 7 | 0 | 2 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & Control | Configuration Audits | 7 | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0
| Access Permissions | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
| Backups | 4 | 0 | 1 | 1 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0
| Change Management | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0
| Metrics | 14 | 1 | 3 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0
| Risk Management | 5 | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0
| Issue Management | 3 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
| Actiion Item Tracking | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Review Defect Tracking | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Test Defect Tracking | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Internal Audit Findings Tracking | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0
| Trainings | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
| Status Reviews | 18 | 3 | 1 | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0
Test Requirements | Requirements Development | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Analysis and Validation | 5 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Traceability | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test Design | DAR | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0
| Product Integration Plan | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0
| Test Plan | 9 | 0 | 1 | 1 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0
| Unit Test Cases | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0
| Integration Test Cases | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0
| System Test Cases | 5 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0
| Regression Test Cases | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0
Test Automation | Load/Performance Test Scenarios | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0
| Automation Framework | 3 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0
| User Documentation | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0
Testing | Build for Integration Testing | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0
| Integration Testing | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0
| Build for System Testing | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0
| System Testing | 5 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0
| Build for Regression Testing | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0
| Regression Testing | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0
| Build for Load/Performance Testing | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0
| Load/Performance Testing | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0
Delivery | Acceptance | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Closure | Project Closure activities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue Leakage Reduction Compliance
| Revenue Leakage Reduction Area | Cycle 1 Applicable Weightage | Cycle 1 |  |  | Cycle 2 Applicable Weightage | Cycle 2 |  |  | Cycle 3 Applicable Weightage | Cycle 3 |  |  | Cycle 4 Applicable Weightage | Cycle 4 |  |  | Cycle 5 Applicable Weightage | Cycle 5
| Preventive compliance | 26 | 5 |  |  | 29 | 0 |  |  | 5 | 0 |  |  | 5 | 0 |  |  | 5 | 0
| Detective compliance | 16 | 3 |  |  | 124 | 0 |  |  | 110 | 0 |  |  | 110 | 0 |  |  | 110 | 0
| Internal Failure compliance | 0 | 0 |  |  | 72 | 0 |  |  | 66 | 0 |  |  | 66 | 0 |  |  | 66 | 0
| External Failure compliance | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| Area | Cycle 1 Applicable Weightage | Cycle 1 |  |  | Cycle 2 Applicable Weightage | Cycle 2 |  |  | Cycle 3 Applicable Weightage | Cycle 3 |  |  | Cycle 4 Applicable Weightage | Cycle 4 |  |  | Cycle 5 Applicable Weightage | Cycle 5
| Plan | 154 | 44 |  |  | 168 | 0 |  |  | 10 | 0 |  |  | 10 | 0 |  |  | 10 | 0
| Do/Implement | 73 | 25 |  |  | 124 | 0 |  |  | 81 | 0 |  |  | 81 | 0 |  |  | 81 | 0
| Check/Verify | 61 | 38 |  |  | 258 | 0 |  |  | 224 | 0 |  |  | 224 | 0 |  |  | 224 | 0
| Act/Improve | 5 | 4 |  |  | 18 | 0 |  |  | 15 | 0 |  |  | 15 | 0 |  |  | 15 | 0

## Risks
BUSINESS RISKS BASED ON PROJECT PROCESS COMPLIANCE STATUS
Area | Risk | Business Impact | Probability of occurrence | Business Impact | Business Risk Score | Severity | Mitigation Plan(s)
Estimations | 1. Risk of improper planning & scheduling due to lack of estimation and/or re-estimation of project effort and schedule. 2. Risk of increased unplanned activities in the project. | 1. Deviation in project schedules. 2. Increase in project cost of production. 3. Increased project overheads. 4. Project profitability may reduce. 5. Decrease in customer satisfaction & customer delight. |  |  | 0 |  | Conduct estimation/re estimation and prepare/update schedule.
Tailoring | Non-compliance to project processes based on existing QMS processes. | 1. Increase in process compliance issues. 2. Low project team and project process productivity. 3. Increased project quality costs. |  |  | 0 |  | Based on project requirements, identify project process tailoring needs and get the approval from SEPG. Implement the project based on project process.
Schedules | 1.Lack of detailed scheduling resulting unplanned activities. 2.Lack of effective control over the project in an objective manner. 3. Lack of employee productivity/efficiency details. | 1.Increased employee workload due to poor scheduling and unplanned activities affecting the employee morale. 2. Loss of opportunity of eliminate non-value added activities. 3. Loss of opportunity to gauge the employee productivity to lack of scheduling assigning tasks and capturing the effort. 4. Imbalance of work among team members affecting the team work. 5. Poor quality of deliverables due to excessive workload on employees. 6. Low employee productivity/efficiency due to poor scheduling and unplanned activities. 7.Failure in delivering business value. |  |  | 0 |  | Prepare project schedules based on QMS guidelines Periodically capture the efforts of project team members
Skill Assessment | Project team members with inadequate skills. | 1. Development of work products with poor quality. 2. Increase in cost of production. 3. Increase in no. of defects during product development. 4. Increase in no. of defects during production. 5. Increase in rework effort and rework cost due to work products with poor quality. 6.Under utilization and low productivity of team members. |  |  | 0 |  | Conduct skill assessment to project resources based on project requirements and plan for trainings.
Backup Plan | 1. Loss of project data due to crash of system/server. | 1.Failure of project data may hamper appropriate deliverables to customer and project. 2. Decrease in customer satisfaction & customer delight due to poor delivery. 3. Decrease in no. of repetitive orders from the customer. 4. Decrease in customer references. 5. Loss of business and market share. |  |  | 0 |  | Follow up with ICT team and ensure that the project data is being backed up. Periodically conduct restoration of project data and address the issues if any.
Change management, Configuration management, access controls | 1.Risk of control over the requirements given by the customer. 2.Requirements/Scope creep. 3.Poor quality of deliverables. 4.Lack of proper estimations. 5.Lack of control over the project configurable items/intellectual property e.g. source code, scope, design etc. 6. Lack of protection to project configurable items/intellectual property. | 1. Increased development costs due to scope creep and lack of proper basis for development. 2. Low project profitability. 3.Lack of project data security. 4. Loss/corruption to critical project components due to lack of configuration management in place. 5. Lack of control over the intellectual property may impact the deliverables with poor quality. 6. Delivering wrong builds to customer. 7. Increase in effort and production cost to address the post delivery defects. 8. Unauthorized sharing of the intellectual property with competitors. 9. Loss of revenue due to unauthorized changes to the source code based on customer requests. |  |  | 0 |  | Documentation of requirements,evidence the review, approval and baseline of requirements document.
Team effort capturing | 1.Lack of effective control over the project in an objective manner. 2.Lack of employee productivity/efficiency details. | 1.Increased employee workload due to poor scheduling and unplanned activities affecting the employee morale. 2. Loss of opportunity of eliminate non-value added activities. 3. Loss of opportunity to gauge the employee productivity to lack of scheduling assigning tasks and capturing the effort. 4. Imbalance of work among team members affecting the team work. 5. Poor quality of deliverables due to excessive workload on employees. 6. Low employee productivity/efficiency due to poor scheduling and unplanned activities. 7.Failure in delivering business value. |  |  | 0 |  | Periodically capture the efforts of project team members
Metrics capturing & analysis | 1.Lack of basis and transparency for objective evaluation of project status. 2.Lack of visibility of the project status. 3. Lack of control over the project resources, schedule, effort, and cost. | 1.Increase in project cost. 2. Decrease in project profitability. 3. Poor quality of the deliverables. 4. Increase in rework due to poor quality of deliverables. 5. Loss of opportunity to reduce cycle time of production/process. 6. Loss of opportunity to gauge the process productivity. 7. Decrease in customer satisfaction & customer delight. |  |  | 0 |  | Periodically capture and analyze the metrics based on the metrics plan of the project. Periodically conduct the metric analysis reviews by reporting authority.
Risk management | Lack of mechanism to handle any potential un foreseen negative events may impact disrupting the project. | 1.Increase in project disruptions e.g. schedule, effort, cost, quality, customer satisfaction etc. 2.Incidents of statutory & regulatory breaches of the project. 3.Reduction in customer satisfaction, confidence and trust due to the absence of consistent, standardized and robust method to assess, monitor and reduce the risks. 4.Decrease in no. of repetitive orders from the customer. 5.Decrease in customer references. 6.Loss of business and market share. |  |  | 0 |  | Periodically identify and monitor the status of risks.
Issue management | Lack of mechanism to handle any project issue which has occured may negatively impact the project. | 1.Conflicts between functions, team members, team & customer. 2.Decrease in employee morale & team spirit. 3.Decrease in company reputation. 4.Decrease in customer satisfaction. 5.Decrease in no. of repetitive orders from the customer. 6.Decrease in customer references. |  |  | 0 |  | Periodically capture and monitor the status of issues.
Action item tracker | Risk of loosing the critical discussions and the action items agreed for the project. | Impact the timely action on critical project deliverables. Loss of control over project team and stakeholder involvement. |  |  | 0 |  | Track the action items for closure based on target date.
Periodic project status reviews | Risk of loosing an opportunity for management's intervention based on critical project requirements. | Recurrence of issues. Loss of oppurtunity to improve the internal communication between project team and management, to set the expectations. Decrease in company reputation. |  |  | 0 |  | Conduct internal status review meetings and identify action items.
Configuration audits | 1.Lack of control over the project configurable items/intellectual property e.g. source code, scope, design etc. 2. Lack of protection to project configurable items/intellectual property. | 1.Lack of project data security. 2. Loss/corruption to critical project components due to lack of configuration management in place. 3. Lack of control over the intellectual property may impact the deliverables with poor quality. 4. Delivering wrong builds to customer. 5. Increase in effort and production cost to address the post delivery defects. 6. Unauthorized sharing of the intellectual property with competitors. 7. Loss of revenue due to unauthorized changes to the source code based on customer requests. |  |  | 0 |  | Ensure adequate change control over project artifacts.
Review defects Analysis | 1. Risk of loosing process improvement opportunities. 2.Risk of pilferage of defects from one phase to another phase. 3.Risk of poor quality for deliverables. | 1.Low process productivity. 2.Loss of oppurtunity to reduce the system/application variation (increase in reliability). 3.Increase in effort and production cost to address the post delivery defects. 4.Decrease in customer satisfaction & customer delight due to repeated defects. 5.Decrease in no. of repetitive orders from the customer. 6.Decrease in customer references. 7.Loss of business and market share. |  |  | 0 |  | Capture and track all the review defects of work products and analyze the same.
Non-Functional requirements | 1. This may lead to key information being overlooked or deferred for critical business processes. 2. Risk of non-fulfilment of contractual requirements. | 1. Poor response time. 2. Huge rework, increasing the costs. 3. Decrease in customer satisfaction & customer delight due to poor performance of the system. 4. Decrease in no. of repetitive orders from the customer 5. Decrease in customer references. 6. Loss of business and market share. |  |  | 0 |  | Capture and address non-functional requirements of the project.
Requirements clarifications, traceability matrix, requirements analysis | Scope creep. | 1. Increased development costs due to scope creep and lack of proper basis for development. 2. Low project profitability. |  |  | 0 |  | Manage scope changes based on scope change management process.
Release plan, acceptance plan and integration plan | 1.Risk on while releasing the Builds. 2.Risk on improper integration of product component requirements. 3.Risk on control of testing schedules, testing process and test execution coverage. 4.Poor Quality of Deliverables | 1. Poor quality of deliverables. 1.Increase in effort and production cost to address the post delivery defects. 2.Decrease in customer satisfaction & customer delight due to repeated defects. 3.Decrease in no. of repetitive orders from the customer. 4.Decrease in customer references. 5.Loss of business and market share. |  |  | 0 |  | Establish the plans along with the review and approval and baseline of all the plan documents.
Review/internal defects capturing and Analysis | 1. Risk of loosing process improvement opportunities. 2.Risk of pilferage of defects from one phase to another phase. 3.Risk of poor quality for deliverables. | 1.Low process productivity. 2.Loss of oppurtunity to reduce the system/application variation (increase in reliability). 3.Increase in effort and production cost to address the post delivery defects. 4.Decrease in customer satisfaction & customer delight due to repeated defects. 5.Decrease in no. of repetitive orders from the customer. 6.Decrease in customer references. 7.Loss of business and market share. |  |  | 0 |  | Capture and track all the review defects of work products and analyze the same.
`
Note on D3: 0.1-->Very unlikely 0.3-->Unlikely 0.5-->Likely 0.7-->More likely 0.9-->Almost certain 1.0-->Happened
Note on E3: 1-->Least 10-->Highest
Note on F3: Risk score 0-3-->No mitigation required Risk score 3.1 to 7-->Only mitigation required Risk score 7.1 to 10-->Mitigation & contingency plans are required.
Note on G3: Risk score: 0 to 3-->Low Risk score: 3.1 to 5-->Medium Risk score: 5.1 to 7-->High Risk score: 7.1 to 10-->Critical

## Project Initiation
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO 9001:2008 Clause | CMMI v1.2 Goal | ISO 27001:2005 Clause
Statement of Work
1 | Is the SoW/Contract available with the Project Manager? | Critical | 5 |  | Plan | SoW/Contract/MSA etc. | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Is the SoW/Contract latest? | Major | 3 |  | Plan | Latest SoW/Contract/MSA etc. | NA |  | NA | NA | NA | [6 empty] | 7.1
Project Initiation Note
1 | Did you consider lessons learnt and best pratices of similar projects? | Major | 3 | Preventive | Plan | Lessons learnt, Best Practices, etc | NA |  | NA | NA | NA | [6 empty] | 7.1
2 | Project Initiation Number generated? | Critical | 5 |  | Do | Project Initiation Note | Yes |  | NA | NA | NA | [6 empty] | 4.2.4
3 | Is the Project Initiation Note prepared? | Minor | 1 |  | Do | Project Initiation Note | Yes |  | NA | NA | NA | [6 empty] | 4.2.4
Project Kick Off
1 | Is the kick-off meeting been conducted? | Critical | 5 |  | Do | Kick-off PPT, MoM, Action Item Tracker, eMail | Yes |  | NA | NA | NA | [6 empty] | 7.1

## Project Management
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
Assumptions & Constraints
1 | Are the assumptions identified also considering SoW? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Are the Constraints & Critical Dependencies identified also considering SoW? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Estimation
1 | Is the Size of the project estimated based on organizational estimation guidelines? | Major | 3 |  | Plan | Estimation document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Is the Effort of the project estimated based on organizational estimation guidelines? | Critical | 5 |  | Plan | Estimation document | Yes |  | NA | NA | NA | [6 empty] | 7.1
3 | Is the Duration of the project estimated based on organizational estimation guidelines? | Major | 3 |  | Plan | Estimation document | Yes |  | NA | NA | NA
4 | Are the estimates are reviewed and approved? | Major | 3 |  | Check | Version history of Estimation document,Review Log, Review Defect Tracker, eMail/MoM | Yes |  | NA | NA | NA | [6 empty] | 4.2.4
5 | Is the estimation document baselined? | Minor | 1 |  | Act | Version history of Estimation document, Project Baseline Register. | No |  | NA | NA | NA | Baseline Register not updated for Estimation | [5 empty] | 4.2.4
Process Plan/Tailoring
1 | Is the lifecycle identified based on Lifecycle Models and Lifecycle Selection Guidelines? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Are the inputs, entry criteria, outputs, exit criteria and acceptance criteria identified based on the lifecycle identified? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
3 | Is the project execution methodology based on the selected lifecycle identified? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
4 | Is the technical data package identified based on the technical work products of the project? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
5 | Are the process tailoring requirements identified based on tailoring guidelines? | Critical | 5 |  | Plan | Tailoring Record | No |  | NA | NA | NA | Tailoring Requirements to be identified | [5 empty] | 7.1
6 | Are the tailoring requirements approved by SEPG? | Major | 3 |  | Do | SEPG approval email, SEPG approval in Training Record | No |  | NA | NA | NA | [6 empty] | 4.2.4
IT/Human Resource Plan
1 | Are the development, testing, deployment environments and tools identified? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Is the project structure identified depicting the roles based on hierarchy? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
3 | Are the roles and adequate responsibilities identified? E.g.: PM, BA etc | Minor | 1 |  | Plan | PMP document | No |  | NA | NA | NA | Agile based roles to be added | [5 empty] | 7.1
4 | Is the staffing plan prepared based on the roles identified and resource estimates across the lifecycle phases of the project? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Skill Assessment
1 | Are the role based skills required identified for the project? | Major | 3 |  | Plan | Skill Assessment/Skill Master component | No |  | NA | NA | NA | Resource wise skill assesment is not evidenced | [5 empty] | 7.1
2 | Is the gap analysis conducted based on the role based skills available and role based skills required for the project? | Critical | 5 |  | Do | Skill Assessment | No |  | NA | NA | NA | Resource wise skill assesment is not evidenced | [5 empty] | 7.1
3 | Is the training plan prepared based on the role based skill gaps? | Major | 0 | Preventive | Plan | Skill Assessment, Schedule/MPP/Schedule Effort Tracker | No |  | NA | NA | NA | Training Plan not evidenced |  |  | 2015-10-28 |  |  | 7.1
Schedule
1 | Is the Schedule available based on the estimated effort and estimated schedule? | Critical | 5 |  | Plan | Schedule/MPP/Schedule Effort Tracker | No |  | NA | NA | NA | PM & Support Activities schedule to be consolidated |  |  | 2015-10-28 |  |  | 7.1
2 | Is the Schedule contains other tasks like project management, audits, reviews, trainings, meetings, travels etc, other than project tasks? | Major | 3 |  | Plan | Schedule/MPP/Schedule Effort Tracker | NA |  | NA | NA | NA | [6 empty] | 7.1
3 | Is the schedule baselined? | Minor | 1 |  | Act | Version history of Schedule Effort Tracker, Project Baseline Register | NA |  | NA | NA | NA | [6 empty] | 4.2.4
Configuration Management Plan
1 | Are the client supplied items identified along with media, storage location? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.5.4
2 | Are the non-configurable items identified along with location and retention period? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
3 | Are the naming conventions of non-configurable items identified based on the Configuration Management Guidelines? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
4 | Are the configurable items identified along with location, criteria for baseline and change approval details? | Critical | 5 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
5 | Are the naming conventions of configurable items identified based on Configuration Management Guidelines? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
6 | Is the criteria for baseline of configurable items identified based on Configuration Management Guidelines? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
7 | Are the release version numbering identified based on Configuration Management Guidelines? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
8 | Is the configuration status accounting identified based on Configuration Management Guidelines? | Major | 3 |  | Plan | PMP document | No |  | NA | NA | NA | Baseline Register is not updated for all the Configurable Items |  |  | 2015-10-28 |  |  | 7.1
9 | Are plans for configuration audits identified? | Critical | 5 |  | Plan | PMP document | No |  | NA | NA | NA | Configuration Audits not done | [5 empty] | 7.1
Access Permissions
1 | Are the access permissions identified for source code and project documentation? | Critical | 5 |  | Plan | Folder Structure Access Control Levels | Yes |  | NA | NA | NA | [6 empty] | 7.1
Backup Plan
1 | Is the backup plan prepared along with restoration plan and restoration procedures? | Critical | 5 |  | Plan | Backup Plan | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Is the Backup Plan baselined? | Minor | 1 |  | Act | Version history of Backup Plan, Project Baseline Register | Yes |  | NA | NA | NA | [6 empty] | 4.2.4
Change Management Plan
1 | Is the change control mechanism identified based on Configuration Management Guidelines? | Critical | 5 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Metrics Plan
1 | Are the metrics identified based on organizational metrics defined in Quality Manual? | Critical | 5 |  | Plan | Metric Analysis Sheet | No |  | NA | NA | NA | Metrics Plan is incomplete | [5 empty] | 7.1
2 | Are the mechanism to collect, analyze along with responsibility, periodicity identified? | Major | 3 |  | Plan | Metric Analysis Sheet | No |  | NA | NA | NA | Metrics Plan is incomplete | [5 empty] | 7.1
3 | Is the periodicity to conduct customer satisfaction survey identified? | Major | 3 |  | Plan | PMP document, updated Metric Analysis Sheet | No |  | NA | NA | NA | Metrics Plan is incomplete | [5 empty] | 7.1
Work Product Review & Audit Plan
1 | Are the quality reviews and audits planned? | Critical | 5 | Preventive | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Are the technical reviews of work products planned? | Critical | 5 | Preventive | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
3 | Is the work product validation plan identified? | Critical | 5 | Preventive | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Risk Management Plan
1 | Are the risk sources & categories, risk parameters definition identified based on risk management guidelines? | Critical | 5 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Are the risk monitoring intervals identified? | Major | 3 |  | Plan | PMP document | No |  | NA | NA | NA | Responisbility for monitoirng the risks is not identfied | [5 empty] | 7.1
3 | Are risks identified also considering assumptions, constraints & critical dependencies including Sow? | Minor | 1 |  | Plan | Risk Tracker | Yes |  | NA | NA | NA | [6 empty] | 7.1
Stakeholder Commitment Plan
1 | Is the stakeholder commitment plan identified based on the roles identified against each deliverable? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Status Review Plan
2 | Are the status review meetings planned along with periodicity? | Critical | 5 |  | Plan | PMP document | No |  | NA | NA | NA | Status Reporting & Reviews Plan is not updated | [5 empty] | 7.1
DAR Plan
1 | Are the areas where DAR to be applied identified? | Critical | 5 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Are the DAR method and evaluation criteria identified based on DAR guidelines? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Escalation Mechanism
1 | Is the escalation methodology identified? | Major | 3 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Reusable Components
1 | Are the reusable components to be used identified? | Major | 3 | Preventive | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
2 | Are the reusable components to be developed identified? | Major | 3 | Preventive | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Project Closure Plan
1 | Is the project closure plan identified? | Minor | 1 |  | Plan | PMP document | Yes |  | NA | NA | NA | [6 empty] | 7.1
Project Management Baseline
1 | Is the Project Management Plan reviewed by SQA team? | Major | 3 |  | Plan | Version history of PMP document, Review Log, Review Defect Tracker. | No |  | NA | NA | NA | PMP Review comments identified by SQA are not closed |  |  | 2015-10-28 |  |  | 4.2.4
2 | Is the Project Management Plan reviewed and approved at Project level? | Major | 3 |  | Check | Version history of PMP document, Review Log, Review Defect Tracker, approval email/MoM. | No |  | NA | NA | NA | Latest changes to PMP is not reviewed and approved |  |  | 2015-10-28 |  |  | 4.2.4
3 | Is the Project Management Plan baselined? | Minor | 1 |  | Check | Version history of PMP document, Project Baseline Register | No |  | NA | NA | NA | PMP is not baselined |  |  | 2015-10-28 |  |  | 4.2.4
4 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA |  | NA | NA | NA | [6 empty] | 8.2.3

## Monitoring & Control
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
Configuration Audits
1 | Are the non-configurable items being named as per naming conventions? | Minor | 1 |  | Do | Project folder | Yes | [10 empty] | 7.5.1
2 | Are the configurable items being named as per naming conventions? | Minor | 1 |  | Do | Project folder, source code components | Yes | [10 empty] | 7.5.1
3 | Are configuration audits conducted based on plan? | Critical | 5 | Preventive | Do | Updated configuration audit checklist. | No |  |  |  |  | Configuration Audits are not conducted | [5 empty] | 7.5.1
Access Permissions
1 | Are the access permissions being implemented for source code and project documentation? | Major | 3 |  | Do | Implementation observations | Yes | [10 empty] | 7.5.5
Backups
1 | Is the back plan issued to ICT? | Major | 3 |  | Do | eMail | No |  |  |  |  | Backup records are not maintained | [5 empty] | 7.5.5
2 | Is the confirmation received from ICT on the backing up of project data based on backup plan? | Minor | 1 |  | Do | eMail | No | [10 empty] | 4.2.4
3 | Is restoration of project data conducted based on plan? | Major | 3 |  | Do | Restoration findings | NA | [10 empty] | 7.5.5
Change Management
1 | Are change requests documented for scope related changes? | Critical | 5 |  | Do | CR Log | NA | [10 empty] | 7.3.7
2 | Are change requests documented for non-scope related changes? | Minor | 1 |  | Do | CR Log | NA | [10 empty] | 7.3.7
3 | Is the impact analysis being done for change requests? | Critical | 5 |  | Check | Change Impact Analysis | NA | [10 empty] | 7.3.7
4 | Are CRs reviewed and approved internally? | Major | 3 | Appraisal | Check | eMail/MoM | NA | [10 empty] | 7.3.7
5 | Are CRs reviewed and approved by customer? | Critical | 5 | Appraisal | Check | eMail/MoM | NA | [10 empty] | 7.3.7
6 | Are suitable CIs updated due to implementation of Change Request? | Minor | 1 |  | Check |  | NA | [10 empty] | 7.3.7
7 | Is the Traceability Matrix updated for the changes? | Minor | 3 |  | Check | Tracreability Matrix | NA | [10 empty] | 7.3.7
8 | Are obsolete documents/records moved into Obsolete folder? | Minor | 1 |  | Check |  | NA | [10 empty] | 7.3.7
Metrics
1 | Are the Metrics collected and analyzed reguarly as per the plan | Critical | 5 |  | Do | Metric Analysis Sheet | No |  |  |  |  | Metrics for the latest release is not captured | [5 empty] | 8.4
2 | Customer satisfaction survey is conducted as per plan? | Major | 3 |  | Do | CSAT forms | No |  |  |  |  | CSAT not collected for the current period | [5 empty] | 8.2.1
3 | Are the corrective actions, target date for implementation identified for deviated metrics? | Major | 3 |  | Check | Metric Analysis Sheet | No |  |  |  |  | Metrics for the latest release is not captured | [5 empty] | 8.5.2
4 | Are the effectiveness of corrective actions being monitored based on target date? | Major | 3 |  | Act | Metric Analysis Sheet | No |  |  |  |  | Metrics for the latest release is not captured | [5 empty] | 8.5.2
Risk Management
1 | Are the project risks monitored reguarly? | Critical | 5 |  | Check | Risk Register | No |  |  |  |  | Risks to be collected and monitored on regular basis | [5 empty] | 8.1
Issue Management
1 | Are the issues being analyzed and tracked to closure? | Major | 3 |  | Check | Issue Tracker | No |  |  |  |  | Non Technical Issues are not Tracked using Issue Tracker | [5 empty] | 8.1
Actiion Item Tracking
1 | Action items are being tracked for closure | Minor | 1 |  | Check | Action Item Tracker | NA | [10 empty] | 8.1
Review Defect Tracking
1 | Review defects are being tracked for closure | Minor | 1 |  | Check | Action Item Tracker | No |  |  |  |  | Review Defects are not tracked to closure | [5 empty] | 8.1
Test Defect Tracking
1 | Test defects are being tracked for closure | Minor | 1 |  | Check | Action Item Tracker | Yes | [10 empty] | 8.1
Internal Audit Findings Tracking
1 | Internal audit findings are being tracked for closure | Minor | 1 |  | Check | Internal Audit Report | Yes | [10 empty] | 8.1
2 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
Trainings
1 | Project process trainings conducted as per plan? | Major | 3 |  | Do | Training request, Attendance and Feedbacks | Yes | [10 empty] | 6.2.2
Status Reviews
1 | Are the internal Status Review meetings being conducted based on plan? | Major | 3 |  | Check | Internal Status PPT, MoM, Action Item Tracker, eMail | No | [10 empty] | 8.1
2 | Are the customer Status Review meetings being conucted based on plan? | Critical | 5 |  | Check | Customer Status PPT, MoM, Action Item Tracker, eMail | No |  |  |  |  | Latest Status reports are not uploaded in Project Portal | [5 empty] | 8.1
3 | Are the Milestone review meetings being conducted based on plan? | Critical | 5 |  | Check | Milestone Status PPT, MoM, Action Item Tracker, eMail | No |  |  |  |  | Latest Release reports are not uploaded in Project Portal | [5 empty] | 8.1
4 | Are the senior management review meetings being conducted based on plan? | Critical | 5 |  | Check | Sr Mgmt Status PPT, MoM, Action Item Tracker, eMail | No | [10 empty] | 8.1
5 | Are the Metrics Analysis Sheet communicated to SEPG periodically? | Major | 3 |  | Check | Metrics Analysis, eMail | NA | [10 empty] | 4.2.4

## Requirements
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
Requirements Development
1 | Are the custmer business requirements available? | Major | 3 |  | Do | Business requirements, MoMs, etc | Yes |  | NA | NA | NA | User Stories - JIRA | [5 empty] | 7.2.1
2 | Are the test requiremets captured and documented in the standard requirement document? | Critical | 5 |  | Do | Test Requirements Specification document/Test Requirements Specification_Analysis document/Requirements Management System/User Stories, Capabilities, Scenarios in Product Backlog for Scrum, Product Backlog for Sprint | Yes |  | NA | NA | NA | [6 empty] | 7.2.1
3 | Are the automation framework requiremets captured and documented in the standard requirement document? | Major | 3 |  | Do | Test Requirements Specification document/Test Requirements Specification_Analysis document/Requirements Management System/User Stories, Capabilities, Scenarios in Product Backlog for Scrum, Product Backlog for Sprint | Yes |  | NA | NA | NA | [6 empty] | 7.2.1
4 | Is the Requirement Clarifications Log being maintained? | Major | 3 |  | Do | Requirements Clarifiation Log | Yes |  | NA | NA | NA | JIRA - Comment | [5 empty] | 7.2.1
Requirements Analysis and Validation
1 | Are the test and automation framework requirements being analyzed? | Critical | 5 |  | Check | Criteria for analysis/Requirements Analysis Checklist | Yes |  | NA | NA | NA | [6 empty] | 7.2.2
2 | Are the test and automation framework requirements reviewed by SQA team? | Minor | 1 | Appraisal | Check | Version history of SRS document/Test Requirements Specification_Analysis document/Requirements Management System,/Product Backlog for Scrum, Product Backlog for Sprint, Review Log, Review Defect Tracker, eMail | NA |  | NA | NA | NA | [6 empty] | 4.2.4
3 | Are the test and automation framework requirements reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of SRS document/Test Requirements Specification_Analysis document/Requirements Management System/Product Backlog for Scrum, Product Backlog for Sprint, Review Log, Review Defect Tracker, eMail | NA |  | NA | NA | NA | [6 empty] | 4.2.4
4 | Are the test and automation framework requirements reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of Test Requirements Specification_Analysis document/Requirements Management System /Customer Approved Product Backlog for Scrum, Product Backlog for Sprint, User Stories review report, Scenarios review report, Review Log, Review Defect Tracker, eMail | NA |  | NA | NA | NA | [6 empty] | 4.2.4
5 | Are the test and automation framework requirements baselined? | Minor | 1 |  | Check | Version history of SRS document/Requirements Management System /Customer Approved Product Backlog for Scrum, Product Backlog for Sprint, Project Baseline Register | NA |  | NA | NA | NA | [6 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA |  | NA | NA | NA | [6 empty] | 8.2.3
7 | Prototype/PoC being developed to validate the automation framework requirments? | Minor | 1 |  | Check | Prototype/PoC | NA |  | NA | NA | NA | [6 empty] | 7.2.2
Requirements Traceability
1 | Is the Traceability Matrix established? | Critical | 5 |  | Do | Traceability Matrix | Yes |  | NA | NA | NA | [6 empty] | 7.5.3

## Design
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
DAR
1 | Are there any design alternatives available that satisfies the requirements? | Major | 3 |  | Do | DAR Report | NA | [10 empty] | 7.3.2
2 | Are the identified design alternatives documented? | Major | 3 |  | Do | DAR Report | NA | [10 empty] | 7.3.2
3 | Is the best solution selected out of the identified alternatives? | Major | 3 |  | Do | DAR Report | NA | [10 empty] | 7.3.2
Product Integration Plan
1 | Is the Product Integration Plan prepared based on project plan? | Critical | 5 |  | Plan | Product Integration Plan | NA | [10 empty] | 7.3.1
2 | Is the Product Integration Plan reviewed by SQA team? | Minor | 1 | Appraisal | Check | Version history of Product Integration Plan, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Is the Product Integration Plan reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of Product Integration Plan, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
4 | Is the Product Integration Plan baselined? | Minor | 1 |  | Check | Version history of Product Integration Plan, Project Baseline Register | NA | [10 empty] | 4.2.4
5 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
Test Plan
1 | Is the Test Plan prepared based on project plan? | Critical | 5 |  | Plan | Test Plan | Yes | [10 empty] | 7.3.1
2 | Is the Test Plan reviewed by SQA team? | Minor | 1 | Appraisal | Check | Version history of Test Plan, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Is the Test Plan reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of Test Plan, Review Log, Review Defect Tracker, eMail | No |  |  |  |  | Test Plan review records to be maintained | [5 empty] | 4.2.4
4 | Is the Test Plan reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of Test Plan, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
5 | Is the Test Plan baselined? | Minor | 1 |  | Check | Version history of Test Plan, Project Baseline Register | No |  |  |  |  | Baseline register to be updated with latest baseline details | [5 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
Unit Test Cases
1 | Are the Unit Test Cases prepared? | Major | 3 |  | Do | Unit Test Cases/Unit Test Scripts | NA | [10 empty] | 7.3.3
2 | Are the Unit Test Cases reviewed by SQA? | Minor | 1 | Appraisal | Check | Version history of Unit Test Cases/Unit Test Scripts, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Are the Unit Test Case reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of Unit Test Cases/Unit Test Scripts, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.4
4 | Are the Unit Test Case reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of Unit Test Cases/Unit Test Scripts, , Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.6
5 | Are the Unit Test Cases baselined? | Minor | 1 |  | Check | Version history of Unit Test Cases/Unit Test Scripts, Project Baseline Register | NA | [10 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
7 | Is the Traceability Matrix updated based on the details of unit test cases? | Minor | 1 |  | Check | Traceability Matrix | NA | [10 empty] | 4.2.4
Integration Test Cases
1 | Are the Integration Test Cases prepared? | Critical | 5 |  | Do | Integration Test Cases/Test Scripts | NA | [10 empty] | 7.3.3
2 | Are the Integration Test Cases reviewed by SQA? | Minor | 1 | Appraisal | Check | Version history of Integration Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Are the Integration Test Case reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of Integration Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.4
4 | Are the Integration Test Case reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of Integration Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.6
5 | Are the Integration Test Cases baselined? | Minor | 1 |  | Check | Version history of Integration Test Cases, Project Baseline Register | NA | [10 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
7 | Is the Traceability Matrix updated based on the details of integration test cases? | Minor | 1 |  | Check | Traceability Matrix | NA | [10 empty] | 4.2.4
System Test Cases
1 | Are the System Test Cases prepared? | Critical | 5 |  | Do | System Test Cases/Test Scripts | Yes | [10 empty] | 7.3.3
2 | Are the System Test Cases reviewed by SQA? | Minor | 1 | Appraisal | Check | Version history of System Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Are the System Test Case reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of System Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.4
4 | Are the System Test Case reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of System Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.6
5 | Are the System Test Cases baselined? | Minor | 1 |  | Check | Version history of System Test Cases, Project Baseline Register | NA | [10 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
7 | Is the Traceability Matrix updated based on the details of system test cases? | Minor | 1 |  | Check | Traceability Matrix | NA | [10 empty] | 4.2.4
Regression Test Cases
1 | Are the Regression Test Cases prepared? | Critical | 5 |  | Do | Regression Test Cases/Test Scripts | NA | [10 empty] | 7.3.3
2 | Are the Regression Test Cases reviewed by SQA? | Minor | 1 | Appraisal | Check | Version history of Regression Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Are the Regression Test Case reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of Regression Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.4
4 | Are the Regression Test Case reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of Regression Test Cases, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.6
5 | Are the Regression Test Cases baselined? | Minor | 1 |  | Check | Version history of Regression Test Cases, Project Baseline Register | NA | [10 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
7 | Is the Traceability Matrix updated based on the details of regression test cases? | Minor | 1 |  | Check | Traceability Matrix | NA | [10 empty] | 4.2.4
Load/Performance Test Scenarios
1 | Are the load/performance test scenarios prepared? | Critical | 5 |  | Do | Load/performance test scenarios | NA | [10 empty] | 7.3.3
2 | Are the load/performance test scenarios reviewed by SQA? | Minor | 1 | Appraisal | Check | Version history of load/performance test scenarios, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Are the load/performance test scenarios reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of load/performance test scenarios, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.4
4 | Are the load/performance test scenarios reviewed and approved by customer? | Critical | 5 | Appraisal | Check | Version history of load/performance test scenarios, Test Script Review Reports, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.6
5 | Are the load/performance test scenarios generated and baselined? | Minor | 1 |  | Check | Version history of load/performance test scenarios, Project Baseline Register | NA | [10 empty] | 4.2.4
6 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
7 | Is the Traceability Matrix updated based on the details of load/performance test scenarios? | Minor | 1 |  | Check | Traceability Matrix | NA | [10 empty] | 4.2.4
Automation Framework
1 | Are the coding standards identified for test script automation and establishment of automation framework? | Major | 3 | Appraisal | Check | Coding Standards | NA | [10 empty] | 7.3.5
2 | Are the test scripts prepared for automation framework? | Major | 3 | Appraisal | Check | Code Review Criteria/Code Review Checklist, Review Log, Review Defect Tracker | Yes | [10 empty] | 8.3
3 | Are the test scripts and automated framework validated? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
User Documentation
1 | Are the User Manuals/Troubleshooting documents/Installation Guides etc prepared for the project? | Critical | 5 |  | Do | User documentation | NA | [10 empty] | 7.3.3
2 | Are the User Manuals/Troubleshooting documents/Installation Guides etc reviewed by SQA? | Minor | 1 | Appraisal | Check | Version history of user documentation, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 4.2.4
3 | Are the User Manuals/Troubleshooting documents/Installation Guides etc reviewed and approved internally? | Major | 3 | Appraisal | Check | Version history of user documentation, Review Log, Review Defect Tracker, eMail | NA | [10 empty] | 7.3.4
4 | Are the User Manuals/Troubleshooting documents/Installation Guides etc baselined? | Minor | 1 |  | Check | Version history of user documentation, Project Baseline Register | NA | [10 empty] | 4.2.4
5 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA | [10 empty] | 8.2.3
6 | Is the Traceability Matrix updated based on user documentation? | Minor | 1 |  | Check | Traceability Matrix | NA | [10 empty] | 4.2.4

## Testing
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
Build for Integration Testing
1 | Is the build for integration testing named based on naming conventions of Project Management Plan? | Minor | 1 |  | Do | Build Note | NA
2 | Is the build verified in the test environment prior to integration testing? | Major | 5 | Appraisal | Check | Build Readiness Review checklist/Smoke Test Report, Release Summary Report | NA
3 | Is the Build Note issued to testing team along with build for integration testing? | Minor | 1 |  | Do | Build Note, eMail | NA
Integration Testing
1 | Is the integration testing done as based on the Test Plan and Integration Test Cases? | Critical | 5 | Appraisal | Check | Test Defect Tracker, Updated Integration Test Cases | NA
2 | Are the test defects being fixed and closed by the development and testing teams? | Major | 3 | Internal Failure | Check | Test Defect Tracker | NA
3 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA
4 | Are the test defects analyzed for root causes and corrective actions? | Major | 3 | Internal Failure | Act | Test Defect Tracker | NA
Build for System Testing
1 | Is the build for system testing named based on naming conventions of Project Management Plan | Minor | 1 |  | Do | Build Note | NA
2 | Is the build verified in the test environment prior to system testing? | Major | 3 | Appraisal | Check | Build Readiness Review checklist/Smoke Test Report, Release Summary Report | NA
3 | Is the Build Note issued to testing team along with build for system testing? | Minor | 1 |  | Do | Build Note, eMail | NA
System Testing
1 | Is the system testing done as based on the Test Plan and System Test Cases? | Critical | 5 | Appraisal | Check | Test Defect Tracker, Updated System Test Cases | Yes
2 | Are the test defects being fixed and closed by the development and testing teams? | Major | 3 | Internal Failure | Check | Test Defect Tracker | NA
3 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA
4 | Are the test defects analyzed for root causes and corrective actions? | Major | 3 | Internal Failure | Act | Test Defect Tracker | NA
Build for Regression Testing
1 | Is the build for regression testing named based on naming conventions of Project Management Plan | Minor | 1 |  | Do | Build Note | NA
2 | Is the build verified in the test environment prior to regression testing? | Major | 3 | Appraisal | Check | Build Readiness Review checklist/Smoke Test Report, Release Summary Report | NA
3 | Is the Build Note issued to testing team along with build for regression testing? | Major | 3 |  | Do | Build Note, eMail | NA
Regression Testing
1 | Is the regression testing done as based on the Test Plan and Regression Test Cases? | Critical | 5 | Appraisal | Check | Test Defect Tracker, Updated Regression Test Cases | NA
2 | Are the test defects being fixed and closed by the development and testing teams? | Major | 3 | Internal Failure | Check | Test Defect Tracker | NA
3 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA
4 | Are the test defects analyzed for root causes and corrective actions? | Major | 3 | Internal Failure | Act | Test Defect Tracker | NA
Build for Load/Performance Testing
1 | Is the build for load/performance testing named based on naming conventions of Project Management Plan | Minor | 1 |  | Do | Build Note | NA
2 | Is the build verified in the test environment prior to load/performance testing? | Major | 3 | Appraisal | Check | Build Readiness Review checklist/Smoke Test Report, Release Summary Report | NA
3 | Is the Build Note issued to testing team along with build for load/performance testing? | Minor | 1 |  | Do | Build Note, eMail | NA
Load/Performance Testing
1 | Is the load/performance testing done as based on the Test Plan and scenarions/scripts? | Critical | 5 | Appraisal | Check | Load/performance test results | NA
2 | Are the test defects being fixed and closed by the development and testing teams? | Major | 3 | Internal Failure | Check | Load/performance test results | NA
3 | Is the rework effort being captured? | Major | 3 | Internal Failure | Check | Schedule effort tracker/MPP/Timesheet | NA
4 | Are the test defects analyzed for root causes and corrective actions? | Major | 3 | Internal Failure | Act | Load/performance test results | NA

## Delivery
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
Acceptance
1 | Is the Test Results Review Report issued to customer upon completion of testing? | Critical | 5 |  | Do | Delivery Note, Test Results Review Report, eMail | Yes |  | NA | NA | NA | [6 empty] | 4.2.4
2 | Is the customer validated the delivery and accepted? | Critical | 5 | Appraisal | Check | Closure Status of User Stories by the Customer in Test Defect Tracker, Signed-off Acceptance Note, Approval email. | Yes |  | NA | NA | NA | [6 empty] | 7.3.6

## Project Closure
S.No | Area/Task/Activity | Criticality | Wtg | COQ | PDCA | Evidences | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Cycle 5 | Description of Finding | Root Cause | Corrective Action | Follow up Audit Date | Actual Closure Date | Closure Comments | ISO Clause Ref | CMMI v1.2 Goal | ISO 27001:2005 Clause
Area: Project Closure
1 | Has the final deliverable (including source, other documentation as agreed upon in SOW / Proposal / Contract) been made? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
2 | Has the project acceptance sign off been obtained from customer? | Critical | 5 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
3 | Are all the NC's that are identified during the Audit are closed? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
4 | All the Change Request (CR) are addressed and closed appropriately. | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
5 | Has the project feedback form been sent to customer? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
6 | Are the Best Practices, Lessons learnt,Sample artifacts,Risk register is moved to Process asset library? | Major | 3 |  | Act |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
7 | Have all technical documents been synchronized with what had been delivered to customer? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
8 | Has the re-estimation of Size and Effort been carried out and variation captured? | Major | 3 |  | Act |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
9 | Have all customer-supplied materials been returned? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
10 | Have all the project members been released? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
11 | Have all the hardware and software resources been released? | Major | 3 |  | Check |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
12 | Project Directory archived | Major | 3 |  | Act |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
13 | Project marked as Closed in project database? | Major | 3 |  | Act |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
14 | Metrics data collection completed? | Major | 3 |  | Act |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1
15 | Have all the reusable components moved to the Process Database? | Major | 3 |  | Act |  | NA | NA | NA | NA | NA | [6 empty] | 7.5.1

## ISO90012008
ISO 9001:2008 Clause wise Audit Findings Status
Project Initiation | [7 empty] | Project Management
ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5 | ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5
Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Records (4.2.4) | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Records (4.2.4) | 8 | 2 | 5 | 0 | 0 | 0 | 0
Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project planning (7.1) | 4 | 2 | 0 | 0 | 0 | 0 | 0 | Project planning (7.1) | 46 | 32 | 13 | 0 | 0 | 0 | 0
Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev validation (7.3.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev validation (7.3.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of production & service provision (7.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of production & service provision (7.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer property (7.5.4) | 1 | 1 | 0 | 0 | 0 | 0 | 0
Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of processes (8.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of processes (8.2.3) | 1 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 6 | 4 | 0 | 0 | 0 | 0 | 0 | Total | 56 | 35 | 18 | 0 | 0 | 0 | 0
Monitoring & Control | [7 empty] | Requirements
ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5 | ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5
Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Records (4.2.4) | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Records (4.2.4) | 4 | 0 | 0 | 0 | 0 | 0 | 0
Skill assessment (6.2.2) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project planning (7.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project planning (7.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Determination of customer requirements (7.2.1) | 4 | 4 | 0 | 0 | 0 | 0 | 0
Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review of requirements (7.2.2) | 2 | 1 | 0 | 0 | 0 | 0 | 0
Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev validation (7.3.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev validation (7.3.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of design & dev changes (7.3.7) | 8 | 0 | 0 | 0 | 0 | 0 | 0 | Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of production & service provision (7.5.1) | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Control of production & service provision (7.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identification & traceability (7.5.3) | 1 | 1 | 0 | 0 | 0 | 0 | 0
Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preservation of product (7.5.5) | 3 | 1 | 1 | 0 | 0 | 0 | 0 | Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan, implement, monitor, measure, analyze & improve processes (8.1) | 10 | 2 | 7 | 0 | 0 | 0 | 0 | Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer satisfaction (8.2.1) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of processes (8.2.3) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of processes (8.2.3) | 1 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis of data (8.4) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corrective action (8.5.2) | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 32 | 6 | 14 | 0 | 0 | 0 | 0 | Total | 12 | 6 | 0 | 0 | 0 | 0 | 0
Design & Coding | [7 empty] | Testing
ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5 | ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5
Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Records (4.2.4) | 25 | 0 | 2 | 0 | 0 | 0 | 0 | Records (4.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project planning (7.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project planning (7.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev planning (7.3.1) | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev inputs (7.3.2) | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev outputs (7.3.3) | 6 | 1 | 0 | 0 | 0 | 0 | 0 | Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev reviews (7.3.4) | 6 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev verification (7.3.5) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev validation (7.3.6) | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev validation (7.3.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of production & service provision (7.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of production & service provision (7.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of processes (8.2.3) | 9 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of processes (8.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of nonconforming product (8.3) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 58 | 3 | 2 | 0 | 0 | 0 | 0 | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Build & Delivery | [7 empty] | Project Closure
ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5 | ISO 9001:2008 Clauses wise | Total Count | Compliance Count | Non Compliance Count Cycle 1 | Non Compliance Count Cycle 2 | Non Compliance Count Cycle 3 | Non Compliance Count Cycle 4 | Non Compliance Count Cycle 5
Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Documentation (4.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Records (4.2.4) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Records (4.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Skill assessment (6.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Infrastructure (6.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work environment (6.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project planning (7.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project planning (7.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Determination of customer requirements (7.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review of requirements (7.2.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer communication (7.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev planning (7.3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev inputs (7.3.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev outputs (7.3.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev reviews (7.3.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design & dev verification (7.3.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & dev validation (7.3.6) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Design & dev validation (7.3.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of design & dev changes (7.3.7) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of production & service provision (7.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of production & service provision (7.5.1) | 15 | 0 | 0 | 0 | 0 | 0 | 0
Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Validation of processes for production & service provision (7.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identification & traceability (7.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer property (7.5.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preservation of product (7.5.5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of monitoring & measuring equipment (7.6) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan, implement, monitor, measure, analyze & improve processes (8.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer satisfaction (8.2.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of processes (8.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of processes (8.2.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitoring & measurement of product (8.2.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control of nonconforming product (8.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analysis of data (8.4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Continual improvement (8.5.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Corrective action (8.5.2) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preventive action (8.5.3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Total | 15 | 0 | 0 | 0 | 0 | 0 | 0
Severity | Wtg
Critical | 5
Major | 3
Minor | 1

## Usage Guidelines
1 | Do not change or tamper the cells with formulae
2 | While conducting the audit for a particular cycle, if the corresponding audit item is complying, change the status to Yes from NA.
3 | If the corresponding audit item is not complying, change the status to No from NA; update the Description of Finding mentioning Cycle # and Date.
4 | During next cycle of audit, it the item which was previously compying, and found not complying during next cycle, then change the respective status to No from NA (previous cycle's status remains Yes).
Now under Description of Finding, mention the deficiency along with Cycle # and Date.
5 | Update the Root Cause, Corrective Action mentioning the Cycle # and Date
6 | Once the audit finding is closed, update the Actual Closure Date along with Closure Comments mentioning the Cycle # and Date